| ##### WORKPACKAGES | #### Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Initial Stability Coding |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Initial Closed User Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Changes as a result of initial user testing |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Planning and building pilot wizards with partners |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Arranging and Running pilots |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Evaluation of pilots |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Updating WCKER from Alpha to Beta version as a result of evaluation feedback |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Peer Review |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Final Reports |  |  |  |  |  |  |  |  |  |  |  |  |  |

Project start date: 18-05-2005

Project completion date: 31-03-2006

Duration: [11] months

| ## Workpackage and activity | ## Earliest ## start ## date | ## Latest completion date | Outputs (clearly indicate deliverables & reports in bold) | Milestone | Responsibility |
| --- | --- | --- | --- | --- | --- |
| ##### WORKPACKAGE 1: Initial Stability Coding | 18/05/05 | 22/07/05 |  |  |  |
| - Finalising Export | 18/05/05 | 22/07/05 | Export finalised |  | DB/TK |
| - Context Dependant Questions | 18/05/05 | 22/07/05 | Context dependant questions resolved |  | DB/TK |
| - Controlled Save Options | 18/05/05 | 22/07/05 | Controlled save options created |  | DB/TK |
| - General Stability | 18/05/05 | 22/07/05 | General stability improved | WCKER ready for user testing | DB/TK |
| ##### WORKPACKAGE 2: Initial Closed User Testing | 20/06/05 | #### 29/07/05 |  |  |  |
| - Identify testers and testing scenarios | 20/06/05 | 22/07/05 | Testers and scenarios identified |  | MM/DW/DB |
| - Design results collection | 20/06/05 | 22/07/05 | Results collection methodology |  | MM |
| - Test WCKER | 22/07/05 | 29/07/05 |  |  | MM/DW/DB |
| - Collect results | 22/07/05 | 29/07/05 |  |  | MM |
| - Report on results and create change requirements list | 22/07/05 | 29/07/05 | Change requirements list | Change requirements specified | MM/DW/DB |
| ##### WORKPACKAGE 3: Changes as a result of initial user testing | 01/08/05 | 12/08/05 |  |  |  |
| - The tasks in this work package will be updated as we get feedback from the initial user testing | 01/08/05 | 12/08/05 | WCKER ready for pilots | WCKER ready for pilots | DB/TK/DW/MT |
| ##### WORKPACKAGE 4: Planning and building pilot wizards with partners | #### 12/08/05 | #### 23/9/05 |  |  |  |
| - Share existing documentation for review | 12/08/05 | 29/7/05 |  |  | MM/TB |
| - initial contact meeting with pilots eLearning team | 12/08/05 | 29/7/05 | Wizard requirements for pilots agreed |  | MM |
| - build sample wizards and share with eLearning team | 1/9/05 | 23/9/05 | Sample wizards |  | DB/TK/MM |
| - Agree final wizards |  | 23/9/05 | Pilot wizards built | Pilot Wizards Built | DB/TK/MM |
| ##### WORKPACKAGE 5: Arranging and Running pilots | #### 08/08/05 | #### 25/11/05 |  |  |  |
| - Identify test scenarios and participants | #### 08/08/05 | 23/9/05 |  |  | Pilots |
| - Train users if required (possible visit here) | #### 08/08/05 | #### 25/11/05 |  |  | MM/TK/DB/MT |
| - Oversee the use of specific wizards | #### 08/08/05 | #### 25/11/05 |  |  | MM/MT |
| - Let partners use WCKER ideally as often as possible | #### 08/08/05 | #### 25/11/05 | WCKER use |  | Pilots |
| ##### WORKPACKAGE 6: Evaluation of pilots | 01/08/05 | 16/12/05 |  |  |  |
| - Design evaluation plan | 01/08/05 | 25/11/05 | Evaluation plan |  | MM/JISC pedagogical consultant |
| - Circulate any questionnaires | 25/11/05 | 16/12/05 | Evaluation data |  | MM/TB |
| - Visit partners for focus groups and interviews (possibly among several pilots) | 25/11/05 | 16/12/05 | Evaluation data |  | MM/DW/DB |
| - Write up evaluation and create change requirements list | 25/11/05 | 16/12/05 | Evaluation report | Evaluation | MM/DW/DB |
| WORKPACKAGE 7: Updating WCKER from Alpha to Beta version as a result of evaluation feedback | 28/11/05 | 24/03/06 |  |  |  |
| - The tasks in this work package will be updated as we get feedback from the pilots | 28/11/05 | 24/03/06 | WCKER beta completed | WCKER beta | TK/DB/DW/MT |
| #### WORKPACKAGE 8: Peer Review | 16/12/06 | 07/04/06 |  |  |  |
| - evaluating peer software | 16/12/06 | 07/04/06 |  |  | MM/DW |
| - write peer review | 27/03/06 | 07/04/06 | Peer review report | Peer Review | MM/DW |
| #### WORKPACKAGE 8: Final Report | 27/03/06 | 07/04/06 |  |  |  |
| - write final report | 27/03/06 | 07/04/06 | Final Report | Final report | MM/DW |

Members of Project Team:

DW = David White

MM = Marion Manton

DB = David Balch

TK = Tjitske Kamphuis

TB = Tom Box

MT = Mike Taylor